# 5. The plan to 29 October

Deadline: Thursday 29 October, end of day. By then: code on GitHub, the app live on AWS, and the AI usage logs. The presentation deck follows straight after, for the first week of November.

## The plan on one page

What this shows - Discovery: done. We picked the problem, asked questions and analysed the dataset. - Fri 23 to Sun 25: build and test the whole app on laptops. The AI runs in “mock” mode until Bedrock is ready. - Mon 26 to Wed 28: deploy on AWS, in your planned three deployment days. - Thu 29: submit. Then finish the deck.

## Who does what

What this shows: a suggested split; swap freely. Each person also does some work outside their main role (role convergence counts in the score), and AI agents help in every role (see 07-how-we-work-with-ai-agents.md).

## Day by day

### Fri 23 Oct (today): data, design, start building

| Done / doing | Output |
| --- | --- |
| Analyse the dataset; find the 5 causes | analysis/, docs/03-what-the-data-says.md ✅ |
| Write plain-English docs and architecture | docs/01–07 |
| Build backend (API, analytics, agents in mock mode) | backend/ + tests |
| Build frontend (9 screens) | frontend/ + tests |
| Write AWS deploy scripts with placeholders | infra/ |
| CI on GitHub Actions (tests on every push) | .github/workflows/ |

End of day check: the app runs on a laptop with one command (docker compose up); tests pass.

### Sat 24 Oct: finish and polish the build

| Task | Who (+ AI agent) |
| --- | --- |
| Review every screen as the COO; list fixes | Sravan + UX researcher agent |
| Fix the list; improve charts | Dinesh + frontend developer agent |
| AI evals: order-intake accuracy on sample emails | Sai + test automation agent |
| Browser tests for the main flows | Dinesh + test automation agent |

End of day check: all main flows work end to end locally; no failing tests.

### Sun 25 Oct: tests, security, rehearse locally

| Task | Who (+ AI agent) |
| --- | --- |
| Security scan (dependencies, code) and fixes | Dinesh + AppSec agent |
| Dry-run the deploy scripts against a local Docker setup | Sai + DevOps agent |
| First demo run-through on a laptop; demo script v1 | Sravan |

End of day check: ready to deploy the moment AWS access arrives.

### Mon 26 Oct: AWS day 1, live

| Time | Task |
| --- | --- |
| 09:00 | Check the AWS access: region, IAM permissions, Bedrock Claude access. Raise gaps in the infra group by 10:00 |
| 09:00 | Read the round-2 answers; update assumptions and numbers |
| 10:00–13:00 | infra/scripts: IAM role, S3, ECR, Secrets Manager, RDS |
| 13:00–16:00 | EC2 launch + Docker + Caddy; load data into RDS; switch AI to Bedrock |
| 16:00–18:00 | Connect Amplify to GitHub; smoke-test the live URL |

End of day check: the live Amplify URL works end to end with real Claude.

### Tue 27 Oct: AWS day 2, automate and watch

Task

GitHub Actions: test → build → push to ECR → deploy to EC2

CloudWatch: log groups, alarms, a small dashboard

Browser tests against the live URL

Fill the ROI story with any new numbers from the round-2 answers

End of day check: a push to main updates the live app automatically.

### Wed 28 Oct: AWS day 3, harden and prove

Task

Security review: IAM least privilege, security groups, RDS not public, encryption

Evidence pack: test reports, AI eval scores, screenshots, security scan results

AI usage logs complete for every role (ai-logs/)

Two timed demo rehearsals on the live URL; record a backup video

Code freeze: tag v1.0

End of day check: everything for submission is ready.

### Thu 29 Oct: submit

- Submit the repo link, the live URL and the AI logs before end of day.

- Keep AWS running for the Round 1 check.

- Build the deck in the required 7-section order.

## What could go wrong, and our backup

| Risk | Backup |
| --- | --- |
| AWS access is late on Monday | The app runs on laptops, so we can demo locally and deploy within hours once access arrives |
| Bedrock Claude not enabled | “Mock” AI mode keeps everything working; we ask L&D to enable the model |
| The browser blocks the API (HTTP vs HTTPS) | Caddy gives HTTPS automatically; backup is an Amplify proxy rule |
| Scope too big | Must-haves first (the Round 1 checklist); extra screens only after |
| Demo fails live | Backup video and a “reset demo data” button |